## MT (hidden)
GOVERNMENT OF TELANGANA
PANCHAYAT RAJ ENGINEERING DEPARTMENT
CHECK SLIP FOR EXTENSION OF AGREEMENT TIME (EOAT)
1 | District | : | Mahabubnagar
2 | Circle | : | Mahabubnagar
3 | Division | : | Narayanpet
4 | Sub-Division | : | Makthal
5 | Section | : | Narwa
6 | Work Identity Number | : | Package No.AP11 1210 - T03
7 | Name of the Work | : | Providing BT on R/F Kalwal to Narwa via Seepur & Raikode, Narwa (M)
8 | Grant/Scheme | : | PMGSY - II
9 | Reference to the Administrative Sanction | : | G.O.Ms.No.33, dt.15.02.2014 of PR & RD (Progs-II) Department for 831.99 Lakhs
10 | Estimated cost | : | Rs. 831.99 Lakhs
11 | Tech/Approval date | : | 2014-02-22
12 | Reference to the Technical Sanction | : | TSR No. /2013-14, dt.22.02.2014 of ENC PR PMGSY Hyderabad for Rs. 550.00 Lakhs. Revised Technical Sanction TSR No. /15-16, dt.16.10.2015 of CE(PR) , PMGSY Hyderabad for Rs.580.00 Lakhs Re-Revised Technical Sanction TSR No. /2017-18, dt 16.05.2017, of CE(PR), PMGSY Hyderabad for Rs. 650.00 Lakhs
13 | Tenders Approved by | : | Engineer in Chief PR Hyderabad
14 | Date of Approval | : | 2014-09-18
15 | Whether Item rate/Percentage rate | : | Percentage Rate
16 | Tender Premium | : | 10.35 % less than the estimated rates of SSR (2013-14)
17 | Contract value | : | 67611918
18 | Name of the Contractor | : | M/s Bhavani Constructions, (Firm No.01701 of 1991), H.No.16-6-114, Nellore, SPSR Nellore District
19 | Date of Agreement | : | 2014-10-25
20 | Date of handover site | : | 2014-10-26
21 | Period of Contract | : | 18 Months
22 | Value of Work done upto Agreement period | : | 8391000
23 | Cost of Work completed in terms of % | : | 15.95%
24 | Value of Work done beyond Agreement period ( with in exempted) | : | 44556815
25 | Value of Work yet to be done | : | 14664103
26 | Agreed date of completion | : | 2016-04-24
27 | Extension of time give earlier if any reference No. & authority | : | Memo Vide no.W23/DEE3/PMGSY-II/Pkg No.111210/Kalwal/2014,dated 12-12-2016 by the Chief Engineer, PR PMGSY Hyd
Proc.No.AEE1/DEE2/PMGSY-II/Package No. AP111210/Kalwal/2017-18, dated 12.10.2017 by the Chief Engineer, PR PMGSY Hyd
28 | Fine Imposed in past | : | 281000
29 | Fine recovered in past | : | 281000
30 | Reasons, if fine was not already recovred and names of Officers responsible | :
31 | EOAT,Now sought upto | : | 2018-03-31
32 | No. of days | : | 304 |  | 2017-05-31
33 | Exemption recommended by the S.E. | :
| Reason |  | The embankment is under submergence in the backwater of MI tank
:
34 | Total days of exemption recommended by the S.E. | : | 133
35 | No. of days to be penalised (32-33) | : | 4
36 | Rate of penalty per day as per agreement clause | :
37 | Total penalty | :
38 | Reasons given by the Contractor | : | The concerned sarpanches have discussed with ayacutdhars and suceeded in getting the land for laying the road and dispute problem is solved.
39 | Recommended | :
| a. AEE/AE | : | EOAT may be granted upto 15.10.2017
| b. DEE | :
| c. EE | : | As stated by the field engineers and the contractor the penalty may be imposed for 04 (four) days
40 | Authority competent to grant EOAT | :
| Asst. Exe Engineer |  | Dy.Executive Engineer, | Executive Engineer
| PR SD Makthal |  | PR SD Makthal | PR Divn Narayanpet
41 | Final recommendation | : | EOAT for the work

## Kollur
GOVERNMENT OF TELANGANA
PANCHAYAT RAJ ENGINEERING DEPARTMENT
CHECK SLIP FOR EXTENSION OF AGREEMENT TIME (EOAT)
1 | District | :
2 | Circle | :
3 | Division | :
4 | Sub-Division | :
5 | Section | :
6 | Work Identity Number | :
7 | Name of the Work | :
8 | Grant/Scheme | :
9 | Reference to the Administrative Sanction | :
10 | Estimated cost | :
11 | Tech/Approval date | :
12 | Reference to the Technical Sanction | :
13 | Tenders Approved by | :
14 | Date of Approval | :
15 | Whether Item rate/Percentage rate | :
16 | Tender Premium | :
17 | Contract value | :
18 | Name of the Contractor | :
19 | Date of Agreement | :
20 | Date of handover site | :
21 | Period of Contract | :
22 | Value of Work done upto Agreement period | :
23 | Cost of Work completed in terms of % | :
24 | Value of Work done beyond Agreement period ( with in exempted) | : |  |  | 5000
25 | Value of Work yet to be done | :
26 | Agreed date of completion | :
27 | Extension of time give earlier if any reference No. & authority | :
28 | Fine Imposed in past | :
29 | Fine recovered in past | :
30 | Reasons, if fine was not already recovred and names of Officers responsible | :
31 | EOAT,Now sought upto | :
32 | No. of days | : |  |  | 0
33 | Exemption recommended by the S.E. | :
| Reason |  |  |  |  | 2018-05-28 | 2018-06-10 | 2018-07-31 | 51
:
34 | Total days of exemption recommended by the S.E. | : |  |  |  | 2019-05-27 | 2019-02-02 | 118 | 2019-05-31
35 | No. of days to be penalised (32-33) | :
36 | Rate of penalty per day as per agreement clause | :
37 | Total penalty | :
38 | Reasons given by the Contractor | :
39 | Recommended | :
| a. AEE/AE | :
| b. DEE | :
| c. EE | :
40 | Authority competent to grant EOAT | :
| Asst. Engineer |  | Dy.Executive Engineer | Executive Engineer
| PR MP Utkoor |  | PR SD Makthal | PR Divn Narayanpet
41 | Final recommendation | : | EOAT for the work